Project No: 10192096 | SkyDrive | Risks, Page 1 of 5

Score

Project risk register Risk = Likelihood (1- low likelihood, 5- high likelihood) x Impact (1- low impact, 5- high impact). Risk: 1-8 = Low, 9-15 = Medium, 16-25 = High

| Risk ID | Risk Area | Risk | Cause | Impact | Pre-control |  |  | Mitigation | Post-control |  |  | WP/Owner(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Likelihood | Impact |  |  | Likelihood | Impact | Score |  |
| T1 | Technical | Model uncertainty in EM/thermal/PD for a 1 kV, 18,000 RPM multiphase motor under reduced-pressure operation and integrated spray cooling. | Capability issues of existing sling tools, particularly non-linear magnetic modelling | Losses and insulation stress are under-predicted, causing efficiency shortfall, hotspots and partial discharge that force derating, rework or stator/rotor damage. | 3 | 4 | 12 | Correlate FEM against Epstein/BH and reduced-pressure PD coupon tests, then tune models with dyno telemetry after each build. Lock correlation targets (±5% torque, ±5°C winding) as entry criteria for next design loop. | 2 | 3 | 6 | WP1 & WP2/Design Leads/iNetic & UCL |
| T2 |  | System requirements (duty cycle, DC-link limits, EMI/EMC, cooling, interfaces) are incomplete for target aircraft (eVTOL/eJTO). | Insufficient market information | Architecture misfit drives mass/volume creep and redesign; certification test gaps appear late, creating schedule/cost overrun. | 3 | 3 | 9 | Run OEM/regulator workshops to freeze an SRS and ICD set, stored in PDM with traceability to tests. All changes go through a CCB with schedule/cost impact approval. | 1 | 3 | 3 | WP1/Design Lead/iNetic |
| T3 |  | Selected multi-level inverter topology cannot demonstrate required fault-ride-through and redundancy at 1 kV with SiC devices. | Complexity in design and power electronics circuits | Inability to meet aerospace reliability targets and DO-160/DO-311 expectations triggers redesign and certification slip. | 4 | 4 | 16 | Carry two inverter topologies to PDR with shared gate-drive/PCB footprints, then down-select after HIL fault-injection proves fault-ride-through. Add per-leg isolation (contactors/fuses) and a verified limp-home control mode to maintain limited thrust under single-fault. | 2 | 3 | 6 | WP1/Design Lead/iNetic |
| T4 |  | Additively manufactured spray-cooling channels and hollow conductors fail yield/accuracy targets for aerospace hardware. | Complexity in the manufacturing different parts | Channel blockage/leakage or high pressure-drop causes scrap and redesign, delaying WP3 prototype and increasing cost. | 4 | 4 | 16 | Run DFAM trials with CT-scanned coupons for geometry/ΔP; if yield <90%, switch to brazed inserts with identical interfaces. | 2 | 2 | 4 | WP1/Design Lead/iNetic |
| T5 |  | Delays on Vacoflux laminations, carbon sleeves and HV insulation due to constrained aerospace supply. | Late delivery of assembly components | Motor/inverter builds miss gates and test windows; idle rig time increases cost and pushes milestones. | 3 | 4 | 12 | Place long-lead POs at PDR, dual-source critical items and hold safety stock; pre-approve equivalent materials in BoM. | 2 | 3 | 6 | WP1/PMT/iNetic |
| T6 |  | Delay in components delivery | Necessary license requirements | The project cannot be delivered | 4 | 5 | 20 | Place the order with a supplier, who already obtained the licenses and active in the process. In addition, provided the necessary documentation with actual pictures of the product. | 3 | 4 | 12 | WP2/PMT/iNetic |
| T7 |  | Aerospace-grade SiC/GaN switches/gate-drivers become allocation-limited or slip in availability. | Global silicon chip supply chain bottleneck | Inverter build halts or needs a package swap that cascades into PCB/redesign delays. | 2 | 3 | 6 | Design pin-compatible second sources and derating to allow swaps; place NC/NR buys post-PDR to bridge lead times. | 1 | 2 | 2 | WP2/PMT/iNetic |
| T8 |  | Component deliveries miss dates due to supplier slips or logistics constraints. | Parts cannot be assembled | Critical assembly steps stall and the test window is missed, extending programme burn. | 3 | 4 | 12 | Place long lead time items early, run weekly expediting and keep pre-qualified alternates for hot-swap. | 2 | 2 | 4 | WP3/Project Engineers/iNetic/UCL |

Project No: 10192096 | SkyDrive | Risks, Page 2 of 5

| T9 |  | Measured weight/efficiency of SkyDrive underperforms benchmark targets and business case. | Sub-Assemblies or Assemblies cannot be made without rework | Payload/range benefits erode, and customer value proposition weakens. | 3 | 3 | 9 | Re-optimise weight/efficiency using current dyno data and costed BoM; keep gearbox/cooling as tuneable levers. | 2 | 2 | 4 | WP1 & WP2/Design Lead/iNetic/UCL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T10 | Technical | Incorrect or unclear drawings | Ambiguities or errors in customer-supplied documentation | Assembly errors, rework, technical delays | 4 | 4 | 16 | Clarification with stakeholders | 2 | 3 | 6 | WP1 & WP2/Project Engineers/iNetic/UCL |
| T11 |  | Component delivery delays | Supplier lead times underestimated or logistics issues | Assembly delay, customer dissatisfaction | 4 | 5 | 20 | Order long lead-time parts early; duel-source where possible | 2 | 3 | 6 | WP2/PMT/iNetic |
| T12 |  | Components out of spec or quality issues | Supplier quality issues or incorrect parts delivered | Scrap/rework, delays, cost increase | 4 | 4 | 16 | Incoming quality control checks and supplier QA agreement | 2 | 3 | 6 | WP3/Quality Lead/iNetic |
| T13 |  | The performance and economics of the SkyDrive are not commercially competitive with rivals | The performance and cost of the components will increase the overall cost and reduce the efficiency | The project objectives may not achieve | 2 | 3 | 6 | The SkyDrive topology can be re-optimised if test results are unattractive. Further work can be defined to improve and optimise performance and economic aspects of SkyDrive | 2 | 2 | 4 | WP1/Design Lead/iNetic |
| T14 |  | The SkyDrive and/or test facilities get significantly damaged while testing | Failure in the design, components, assembly, or testing | Delay to the project | 1 | 4 | 4 | Comprehensive instrumentation and protection system will be employed for test programme. Potentially destructive tests will be scheduled for the end of test programme | 1 | 2 | 2 | WP3/Testing Lead/iNetic/ARC |
| T15 |  | Mechanical failure due to rotor hoop stress at 18,000 rpm | Insufficient Validation | Catastrophic rotor burst leading to test bench destruction and major schedule slip | 3 | 5 | 15 | Validate rotor laminations via FEA (stress, modal, fatigue); use high-strength retaining sleeves; staged spin testing to qualified RPMs | 2 | 3 | 6 | WP3/PMT/iNetic |
| T16 |  | Coil winding issues | Winding errors | Electrical failure, safety hazard | 3 | 4 | 12 | Double-checked coil calculator, winding plan, temperature rating validated | 2 | 2 | 4 | WP3/Production/iNetic |
| T17 |  | SkyDrive component overheating | Poor thermal design | System failure or safety risk | 3 | 4 | 12 | Thermal simulations, derating, heatsink validation, UL/CE Certified materials | 2 | 2 | 4 | WP1/Design Lead/UCL |
| T18 |  | Assembly instructions are incomplete or non-intuitive for novel integrated features. | Unclear SOPs (Standard Operating Procedures) | Build mistakes, rework and safety exposure increase, impacting schedule. | 3 | 3 | 9 | Create visual SOPs and train; run supervised pilot build with hold-points and checklists. | 1 | 2 | 2 | WP3/Project Engineer/iNetic |
| T19 |  | Motor/Powertrain fails final testing | Design flaw | Rework, redesign | 3 | 4 | 12 | Simulation, Design Validation Plan (DVP), component level and sub-assemblies testing | 2 | 3 | 6 | WP3/Design and Testing Teams/iNetic |
| T20 |  | Test rig is not ready | Dependency delay | Test delay, project stall | 2 | 4 | 8 | Parallel planning, early test rig preparation | 2 | 2 | 4 | WP3/Testing Team/iNetic and ARC |
| T21 |  | Inadequate Tooling | No early jig plan | Assembly delay, operator workaround | 2 | 4 | 8 | Include fixture planning and implementation in early design stage | 1 | 2 | 2 | WP1/Design Lead/iNetic, UCL |

Project No: 10192096 | SkyDrive | Risks, Page 3 of 5

| T22 |  | Inadequate convective heat transfer from microchannel / oil spray cooling under dynamic loading | Inadequate cooling | Thermal saturation limits continuous power; triggers derating or failsafe shutdown | 2 | 4 | 8 | Perform high-resolution CFD simulations; bench test cooling loop using hardware-in-loop with embedded sensors; incorporate secondary redundant cooling pathway (e.g. hollow copper windings) | 1 | 3 | 4 | WP2/Design Lead/UCL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T23 |  | Thermal Management Under Real Operating Conditions | Overheating of motor or power electronics during continuous or peak load operation | Reduced performance, efficiency, or component damage | 3 | 4 | 12 | Simulation and testing under real flight-like conditions; liquid cooling if needed | 2 | 3 | 6 | All/Design Leads/iNetic/UCL |
| T24 |  | Power Density vs. Reliability Trade-offs | High-performance goals (torque/weight, power/kg) may compromise long-term reliability | Premature failure or inability to meet airworthiness standards | 4 | 4 | 16 | Conservative design margins, accelerated life testing, FMEA | 2 | 3 | 6 | WP1 & WP3/iNetic |
| T25 |  | Noise, Vibration & Harshness (NVH) | Electromagnetic forces or mechanical assembly leading to high NVH levels | Compromised passenger comfort or structural fatigue | 3 | 3 | 9 | Finite element analysis (FEA), NVH testing, precision balancing | 2 | 2 | 4 | WP1/Design Lead/iNetic |
| T26 |  | Precision Manufacturing & Assembly | Tolerances in critical rotating components (e.g. rotors, gears) may not be achievable consistently | Misalignment, performance variation, assembly failure | 4 | 4 | 16 | Rigorous supplier selection, in-house capability (e.g. CMM validation), pilot production | 2 | 3 | 6 | WP3/PMT/iNetic |
| T27 |  | Control System Tuning & Certification | Delays in tuning motor controllers or certifying software for aerospace compliance (e.g. DO-178C) | Major bottleneck in development timeline | 3 | 5 | 15 | Use experienced control partners; modular software architecture | 2 | 3 | 6 | WP3/Testing Lead/iNetic |
| T28 |  | Inadequate Testing Environment | Prototype rigs or test setups may not simulate high-altitude, vibration, or cooling conditions accurately | Performance at system level may deviate from lab results | 3 | 4 | 12 | HIL (Hardware-in-the-Loop) setups, vibration tables, altitude chambers | 2 | 2 | 4 | WP4/Testing Lead/iNetic |
| T29 |  | Compatibility with Battery/Power Source | Mismatch between motor system demands and available battery architecture (voltage, current, stability) | Underperformance or system damage | 3 | 4 | 12 | Define system-level power requirements early, involve battery partners | 2 | 2 | 4 | WP1/Design Lead/iNetic |
| T30 |  | System integration (motor, drive) faces mechanical or software mismatches | Incomplete or Unclear Interface Definition | Test delays; need for rework or additional interface development | 4 | 5 | 20 | Interfaces defined in WP1 and co-developed with ARC; staged test plan from subsystem to bench level | 3 | 4 | 12 | WP3/Testing Lead/iNetic |
| T31 |  | Underperformance of inverter or motor subsystem | Design complexity under thermal/mechanical stress | Key performance metrics not met | 4 | 4 | 16 | Iterative hardware testing (WP4), alternative designs validated in WP1 | 3 | 3 | 9 | WP1 & WP4/Design Lead/UCL |
| T32 |  | Thermal management failures in prototypes | Inadequate heat dissipation | Component failure, test delays | 3 | 4 | 12 | System-level thermal modelling and phased test validation in WP3 | 2 | 3 | 6 | WP4/Design Lead/UCL |
| T33 |  | Assembly errors or lack of skill | Lack of experience with specific rotor design | Functional issues, safety concerns | 3 | 4 | 12 | Training, work instructions, supervised assembly | 1 | 3 | 3 | WP3/ Production Lead/iNetic |

Project No: 10192096 | SkyDrive | Risks, Page 4 of 5

| C34 | Commercial | Failure to meet the specs | Delays in parts, rework, or poor | Penalties, loss of customer | 4 | 5 | 20 | Buffer in schedule | 2 | 3 | 6 | All/PMT/iNetic |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C35 |  | Cost Overrun | Material inflation, unexpected rework, poor quoting | Reduced margin or loss | 3 | 3 | 9 | Tight cost tracking, contingency budget, fixed-price supply deals | 2 | 2 | 4 | WP2/PMT/iNetic |
| C36 |  | Customer Concentration Risk | Heavy reliance on a small number of clients or sectors | High exposure if a single customer or sector withdraws or delays | 3 | 4 | 12 | Diversify target customers, heavy duty application including buses | 2 | 3 | 6 | All/Commercial Lead/iNetic |
| C37 |  | Intellectual Property Risk | Risk of IP infringement or insufficient protection of innovations in motor, controller, or integration | Legal disputes or inability to defend competitive advantage | 3 | 4 | 12 | File patents early; use NDAs; monitor for infringement | 2 | 3 | 6 | All/Commercial Lead/iNetic |
| C38 |  | Misalignment with Customer Roadmaps | SkyDrive may not meet timing, interface, or specification needs of customers | Lost sales opportunities or required redesigns | 3 | 4 | 12 | Co-develop with anchor customers, maintain flexible and modular design | 2 | 2 | 4 | All/Commercial Lead/iNetic |
| C39 |  | Geo-political or Trade Risks | Trade restrictions, export controls, or currency fluctuations could affect global sales and sourcing | Increased cost or lost access to markets/suppliers | 3 | 4 | 12 | Use multiple international suppliers; consider UK/EU/US as independent routes to market | 2 | 3 | 6 | All/Commercial Lead/iNetic |
| C40 |  | Change in customer requirement after build starts | Customer changes design or scope late | Wasted work, rework, negotiation | 3 | 4 | 12 | Lock design at order, change control process | 2 | 2 | 4 | WP1/Project Engineer |

| M41 | Managerial | Resource constraints or skills gaps | Shortage of skilled engineers, certification specialists, or production managers | Delays in design, testing, or certification | 4 | 5 | 20 | Workforce planning, cross-training, partnerships with experienced subcontractors | 3 | 3 | 9 | All/Engineering Manager/iNetic |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M42 |  | Key staff attrition | Competitive job market | Loss of critical expertise | 3 | 4 | 12 | Retention bonuses + cross-training | 2 | 3 | 6 | All/Project Engineer |
| M43 |  | Communication breakdown (internal/external) | Poor flow of information between teams, suppliers, or clients | Misalignment, rework, trust loss | 3 | 4 | 12 | Regular reviews, collaborative tools (e.g. MS Teams, Slack), project dashboard | 2 | 2 | 4 | All/Programme Coordinator/iNetic |
| M44 |  | Inadequate Risk Management Culture | Risks not identified, assessed, or escalated in time | Reactivity to crises rather than proactive management | 4 | 4 | 16 | Risk register, scheduled reviews, escalation matrix | 2 | 3 | 6 | All/Quality Lead/iNetic |
| M45 |  | Delayed Decision-Making | Slow approvals or indecision by management or partners | Bottlenecks in procurement, design freeze, testing | 3 | 4 | 12 | Delegated authority matrix, time-boxed decisions, pre-alignment | 2 | 3 | 6 | All/Steering Committee Chair/iNetic |
| M46 |  | Weak Project Governance | Lack of clear roles, reporting structure, or accountability | Missed KPIs, disjointed execution | 4 | 4 | 16 | RACI charts, governance board, regular performance tracking | 2 | 3 | 6 | All/Project Manager/iNetic |

Project No: 10192096 | SkyDrive | Risks, Page 5 of 5

| M47 | Managerial | Inconsistent Stakeholder Engagement | Stakeholders (govt, funders, potential customers) not kept informed or involved | Loss of support or misaligned expectations | 3 | 4 | 12 | Stakeholder map, newsletters, quarterly briefings/workshops | 2 | 3 | 6 | All/Project Coordinator/iNetic |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M48 |  | Timeline slippage | Unforeseen technical hurdles | Project delays | 3 | 3 | 9 | Milestone buffers + weekly stand-ups | 2 | 2 | 4 | All/Project Engineer |
| M49 |  | Budget overrun | Subcontractor delays | Cost escalation | 2 | 4 | 8 | Fixed-price contracts + contingency fund | 1 | 3 | 3 | All/Project Engineer |
| M50 |  | Data/Documentation loss or miscommunication | Poor version control or lack of clarity in instructions | Assembly errors, delays | 3 | 3 | 9 | Central document control system version | 1 | 2 | 2 | WP3/Project Engineer |
| E51 | Environmental | Rare Earth Magnet Supply & Sustainability | Use of neodymium-based permanent magnets (e.g. N48UH) may involve environmentally damaging mining processes | Ethical sourcing concerns, supply chain instability, reputational risk | 4 | 5 | 20 | Source from ISO 14001-certified suppliers; assess recycled magnet options; disclose sustainability practices | 3 | 3 | 9 |  |
| E52 |  | Energy savings not achieved | Suboptimal scheduling | Higher operational costs | 3 | 3 | 9 | Real-time energy monitoring + AI (Artificial Intelligence) tweaks | 2 | 2 | 4 | WP3/Digital Lead |
| E53 |  | Scrap rate exceeds target | Poor material handling | Increased waste disposal costs | 2 | 4 | 8 | Lean kitting + error-proofing design | 1 | 3 | 3 | WP3/Prod. Engineer |
| S54 | Social | Skills gap in digital manufacturing | Lack of local training programs | Reduced operational efficiency | 2 | 3 | 6 | STEM (Science, Technology, Engineering, Mathematics) workshops | 1 | 2 | 2 | WP3/Production Manager/iNetic |
| S55 |  | Health and Safety incident during assembly | Inadequate H&S measures or untrained staff | Injury, project halt, liability | 2 | 5 | 10 | Central document controls system, version control | 1 | 2 | 2 | WP3/Production Manager/iNetic |